## Sheet1
|  |  | Days | step 1 | step 2 | step 3 | step 4 | step 5 | step 6 | step 7 | step 8 | step 9 | step 10 | step 11
A | Job Review | _ | 1 | bar: step 1
B | Advise customers of Temporary Outage | A | 0.5 | bar: step 2
C | Requisition Stores | A | 1 | bar: step 2
D | Scout Job | A | 0.5 | bar: step 2
E | Secure Poles and Materials | C,D | 3 | bar: step 3
F | Distribute Poles | E | 3.5 | bar: step 4
G | Pole location coordination | D | 0.5 | bar: step 3
H | Re-stake | G | 0.5 | bar: step 4
I | Dig Holes | H | 3 | bar: step 5
J | Frame and set poles | F,I | 4 | bar: step 6
K | Cover old conductors | F,I | 1 | bar: step 6
L | Pull new conductors | J,K | 2 | bar: step 7
M | Install remaining material | L | 2 | bar: step 8
N | Sag conductor | L | 2 | bar: step 8
O | Trim Trees | D | 2 | bar: step 3
P | De-Energize and switch lines | B,M,N,O | 0.11111 | bar: step 9
Q | Energize and switch new line | P | 0.5 | bar: step 10
R | Clean up | Q | 1 | bar: step 11
S | Return Material to stores | I | 2 | bar: step 6