STEPS:

- Ask for # of activities.→ X

- Get duration for each activity.

- Ask for # predecessors

- Get each predecessor

Where and how data is stored:

MATRIX A:      {X,9}→dim([A])

Data is stored in rows for each activity, (n, data type #), where n is the current activity number

A (n,1) = duration

A (n,2) = Early Start

A (n,3) = Early Finish

A (n,4) = Late Start

A (n,5) = Late Finish

A (n,6) = Free Float

A (n,7) = Total Float

A (n,8) = INTF

A (n,9) = INDF

MATRIX B, C. {X,8} → dim([B or C])

NOTE:  Largest matrix=50,8 or 400 cells

B is predecessors

After the last predecessor in each row is listed, set remaining cells in row=0

If no predecessor, set entire row=0.

For successors

For(n=I;n≤X;i++){ For loop. Start from top of list.

Set o(increment for matrix C)=1

For(i=1;i≤X;i++){check each activities predecessor and determine if n is predecessor.

For(j=1; j≤8; j++){

If ([B](i,j)==n){

[C](n,o)=i

Break j loop, set j= 8

O++

}

}

}

ESD calculated

if(n,B)==0

set A(n,2)=0

else

if(

if no pre, set star=0

if pre find largest pre and set star to largest pred finish

for loop(

if pred finish time==0 run calculation on it.

EFD calc

A(n,3)=A(n,1)+A(n,2)

LSD calc

A(n,4)=A(n,5)- A(n,1)

For(N,X,1,^-^1)

If [C](N,1)=0

Then

[A](N,3)→[A](N,5)

[A](N,2)→[A](N,4)

End

Else

Then

For(J,1,8,1)

If [C] (N,J)=0

[A](N,4)

Find smallest successor LFD

Set LFD to Successor LSD

FF=min ESDsuc-EFD

A(n,6)=min A(n of suc,2)-A(n,3)

TF=LF-EF

A(n,7)=A(n,5)-A(n,3)

For(N,X,1,1)

[A](N,5)-[A](N,3)→ [A](N,7)

For(J,1,8,1)

If [C](N,J)!=0

Then

If [A]([C] (N,J),2)>0 and[A]([C] (N,J),2)<[A](N,6)

Then

[A]([C] (N,J),2)-[A](N,3)→[A](N,6)

End

End

End

End

INTF=TF-FF

For loop N

[A](N,7)- [A](N,6)→ [A](N,8)

0→L

For(J,1,8,1)

If [C](N,J)≠0

Then

If [A]([C](N,J),2)>0 and [A]([C](N,J),2)<L

Then

[A]([C](N,J),2)→L

End

If L=0 and [A]([C](N,J),2)>0

Then

[A]([C](N,J),2)→L

End

End

End

0→F

For(J,1,8,1)

If [B](N,J)≠0

Then

If [A]([B](N,J),5)>0 and [A]([B](N,J),5)<F

Then

[A]([B](N,J),5)→F

End

If L=0 and [A]([B](N,J),5)>0

Then

[A]([B](N,J),5)→F

End

End

End

L-F-[A](N,1)→[A](N,9)

INDF=min Successor ESD-  min Predecessor LFD – DUR

A(n,9)=-A(n,1)

Advice:

Smaller classes

More tests

Slower in the network generation, AOA,AON,OVerlapping