EMCH-380 HW #2

# Question 1

Critical Paths: B,E,J,M; C,G,L,N

A,D,H,M: 19wks

A,I,M: 17 wks

C,F,K,N: 16 wks

| # | ACT. | DUR | PRED. | ESD | EFD | LFD | LSD | Slack |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Start | 0 | - | 0 | 0 | 0 | 0 | 0 |
| 2 | A | 6 | 1 | 0 | 6 | 7 | 1 | 1 |
| 3 | B | 3 | 1 | 0 | 3 | 3 | 0 | 0 |
| 4 | C | 4 | 1 | 0 | 4 | 4 | 0 | 0 |
| 5 | D | 4 | 2 | 6 | 10 | 11 | 7 | 1 |
| 6 | E | 7 | 3 | 3 | 10 | 10 | 3 | 0 |
| 7 | F | 4 | 4 | 4 | 8 | 12 | 8 | 4 |
| 8 | G | 6 | 4 | 4 | 10 | 10 | 4 | 0 |
| 9 | H | 3 | 5 | 10 | 13 | 14 | 11 | 1 |
| 10 | I | 5 | 2 | 6 | 11 | 14 | 9 | 3 |
| 11 | J | 4 | 6 | 10 | 14 | 14 | 10 | 0 |
| 12 | K | 3 | 7 | 8 | 11 | 15 | 12 | 4 |
| 13 | L | 5 | 8 | 10 | 15 | 15 | 10 | 0 |
| 14 | M | 6 | 9,10,11 | 14 | 20 | 20 | 14 | 0 |
| 15 | N | 5 | 12,13 | 15 | 20 | 20 | 15 | 0 |
| 16 | Finish | 0 | 14,15 | 20 | 20 | 20 | 20 | 0 |

- Must Focus on Tasks with 0 slack, So, Focus on B,C,E,G,J,L,M,N

# QUESTION 2

- Set up a table, and without drawing the network diagram, compute the schedule dates         (ESD, EFD).

| ACT | DUR | ESD | EFD |
| --- | --- | --- | --- |
| A | 2 | 0 | 2 |
| B | 3 | 2 | 5 |
| C | 6 | 2 | 8 |
| D | 5 | 2 | 7 |
| E | 9 | 5 | 14 |
| F | 7 | 8 | 15 |
| G | 2 | 8 | 10 |
| H | 4 | 7 | 11 |
| J | 3 | 15 | 18 |
| K | 5 | 15 | 20 |
| L | 2 | 11 | 13 |
| M | 7 | 20 | 27 |
| N | 4 | 20 | 24 |
| P | 2 | 27 | 29 |

- Compute the lag for each link and identify activities on the critical path.

| Link | LAG | Link | LAG |
| --- | --- | --- | --- |
| A-B | 0 | G-K | 5 |
| A-C | 0 | H-K | 4 |
| A-D | 0 | G-L | 1 |
| B-E | 0 | H-L | 0 |
| B-F | 3 | J-M | 2 |
| C-F | 0 | K-M | 0 |
| C-G | 0 | K-N | 0 |
| D-H | 0 | L-M | 7 |
| E-J | 1 | L-N | 7 |
| F-J | 0 | M-P | 0 |
| G-J | 5 | N-P | 3 |
| F-K | 0 |  |  |

Activities on Critical Path

A, C, F, K, M, P

- Compute the four floats (TF, FF, INTF, INDF) for each activity.

| ACT | DUR | ESD | EFD | LFD | LSD | FF | TF | INTF | INDF |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| A | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 |
| B | 3 | 2 | 5 | 8 | 5 | 0 | 3 | 3 | 0 |
| C | 6 | 2 | 8 | 8 | 2 | 0 | 0 | 0 | 0 |
| D | 5 | 2 | 7 | 11 | 6 | 0 | 4 | 4 | 0 |
| E | 9 | 5 | 14 | 17 | 8 | 1 | 3 | 2 | -2 |
| F | 7 | 8 | 15 | 15 | 8 | 0 | 0 | 0 | 0 |
| G | 2 | 8 | 10 | 15 | 13 | 1 | 5 | 4 | 1 |
| H | 4 | 7 | 11 | 15 | 11 | 0 | 4 | 4 | -4 |
| J | 3 | 15 | 18 | 20 | 17 | 2 | 2 | 0 | 2 |
| K | 5 | 15 | 20 | 20 | 15 | 0 | 0 | 0 | 0 |
| L | 2 | 11 | 13 | 20 | 18 | 7 | 7 | 0 | 3 |
| M | 7 | 20 | 27 | 27 | 20 | 0 | 0 | 0 | 0 |
| N | 4 | 20 | 24 | 27 | 23 | 3 | 3 | 0 | 3 |
| P | 2 | 27 | 29 | 29 | 27 | 0 | 0 | 0 | 0 |

# QUESTION 3

Determine the critical path for each of the project networks shown below. Compute the four floats for each of the activities in the network. (TF, FF, INTF, INDF)

CRITICAL PATHS

1-2-3-4-6-7

| i-j | Duration | ESD | EFD | LFD | LSD | FF | TF | INTF | INDF |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1-2 | 10 | 0 | 10 | 10 | 0 | 0 | 0 | 0 | 0 |
| 1-5 | 5 | 0 | 5 | 20 | 15 | 13 | 15 | 2 | 0 |
| 1-4 | 1 | 0 | 1 | 22 | 21 | 21 | 21 | 0 | 0 |
| 2-5 | 8 | 10 | 18 | 20 | 12 | 0 | 2 | 2 | 0 |
| 2-6 | 10 | 10 | 20 | 27 | 17 | 7 | 7 | 0 | 7 |
| 2-3 | 9 | 10 | 19 | 19 | 10 | 0 | 0 | 0 | 0 |
| 4-6 | 5 | 22 | 27 | 27 | 22 | 0 | 0 | 0 | 0 |
| 4-7 | 4 | 22 | 26 | 35 | 31 | 9 | 9 | 0 | 9 |
| 3-6 | 4 | 19 | 23 | 27 | 23 | 4 | 4 | 0 | 4 |
| 3-4 | 3 | 19 | 22 | 22 | 19 | 0 | 0 | 0 | 0 |
| 5-6 | 7 | 18 | 25 | 27 | 20 | 2 | 2 | 0 | 0 |
| 5-7 | 3 | 18 | 21 | 35 | 32 | 14 | 14 | 0 | 12 |
| 6-7 | 8 | 27 | 35 | 35 | 27 | 0 | 0 | 0 | 0 |

Critical Paths

1-4-5-6-7

1-4-5-7

1-4-7

| i-j | DUR | ESD | EFD | LFD | LSD | FF | TF | INTF | INDF |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1-2 | 3 | 0 | 3 | 4 | 1 | 0 | 1 | 1 | 0 |
| 1-3 | 1 | 0 | 1 | 12 | 11 | 10 | 11 | 1 | 0 |
| 1-6 | 7 | 0 | 7 | 30 | 23 | 23 | 23 | 0 | 0 |
| 1-4 | 15 | 0 | 15 | 15 | 0 | 0 | 0 | 0 | 0 |
| 2-3 | 8 | 3 | 11 | 12 | 4 | 0 | 1 | 1 | 0 |
| 2-5 | 10 | 3 | 13 | 25 | 15 | 12 | 12 | 0 | 0 |
| 3-4 | 3 | 11 | 14 | 15 | 12 | 1 | 1 | 0 | 0 |
| 3-7 | 10 | 11 | 21 | 37 | 27 | 16 | 16 | 0 | 0 |
| 4-5 | 10 | 15 | 25 | 25 | 15 | 0 | 0 | 0 | 0 |
| 4-7 | 22 | 15 | 37 | 37 | 15 | 0 | 0 | 0 | 0 |
| 5-6 | 5 | 25 | 30 | 30 | 25 | 0 | 0 | 0 | 0 |
| 5-7 | 12 | 25 | 37 | 37 | 25 | 0 | 0 | 0 | 0 |
| 6-7 | 7 | 30 | 37 | 37 | 30 | 0 | 0 | 0 | 0 |

# QUESTION 4

| i | j | ACT | DUR | ESD | EFD | LFD | LSD | FF | TF | INTF | INDF |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 5 | 10 | S | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 0 | 0 |
| 5 | 15 | R | 3 | 0 | 3 | 4 | 1 | 0 | 1 | 1 | 0 |
| 10 | 20 | A | 5 | 4 | 9 | 9 | 4 | 0 | 0 | 0 | 0 |
| 10 | 25 | E | 2 | 4 | 6 | 7 | 5 | 0 | 1 | 1 | 0 |
| 10 | 30 | d1 | 0 | 4 | 4 | 6 | 6 | 1 | 2 | 1 | 1 |
| 15 | 30 | G | 2 | 3 | 5 | 6 | 4 | 0 | 1 | 1 | -1 |
| 15 | 35 | B | 1 | 3 | 4 | 6 | 5 | 0 | 2 | 2 | -1 |
| 20 | 40 | d2 | 0 | 9 | 9 | 9 | 9 | 0 | 0 | 0 | 0 |
| 20 | 60 | L | 2 | 9 | 11 | 13 | 11 | 0 | 2 | 2 | 0 |
| 25 | 40 | K | 2 | 6 | 8 | 9 | 7 | 1 | 1 | 0 | 0 |
| 25 | 45 | d3 | 0 | 6 | 6 | 12 | 12 | 2 | 6 | 4 | 1 |
| 30 | 45 | C | 3 | 5 | 8 | 12 | 9 | 0 | 4 | 4 | -1 |
| 30 | 50 | H | 6 | 5 | 11 | 12 | 6 | 0 | 1 | 1 | -1 |
| 35 | 45 | d4 | 0 | 4 | 4 | 12 | 12 | 4 | 8 | 4 | 2 |
| 35 | 55 | J | 4 | 4 | 8 | 10 | 6 | 0 | 2 | 2 | -2 |
| 40 | 65 | M | 6 | 9 | 15 | 15 | 9 | 0 | 0 | 0 | 0 |
| 45 | 65 | d5 | 0 | 8 | 8 | 15 | 15 | 7 | 7 | 0 | 3 |
| 45 | 70 | T | 3 | 8 | 11 | 15 | 12 | 2 | 4 | 2 | -2 |
| 50 | 65 | W | 3 | 11 | 14 | 15 | 12 | 1 | 1 | 0 | 0 |
| 50 | 70 | d6 | 0 | 11 | 11 | 15 | 15 | 2 | 4 | 2 | 1 |
| 55 | 70 | X | 5 | 8 | 13 | 15 | 10 | 0 | 2 | 2 | -2 |
| 60 | 75 | N | 6 | 11 | 17 | 19 | 13 | 2 | 2 | 0 | 0 |
| 65 | 75 | P | 4 | 15 | 19 | 19 | 15 | 0 | 0 | 0 | 0 |
| 70 | 75 | V | 4 | 13 | 17 | 19 | 15 | 2 | 2 | 0 | 0 |

- Setup a table and without drawing the network diagram, compute the four schedule dates (ESD, EFD, LFD, LSD) and the four floats (TF, FF, INTF, INDF).

- Identify the activities on the critical path and the project duration.

PROJECT DURATION: 19 DAYS

CRITICAL PATH:  5-10-20-40-65-75