## Slide 1: Honicker Corporation
Group 1
By: Jacob Vaught, Kyle Wagar, Robert Sposato, Greg Richard, Forrest Donnellan, and Chen Carson.

## Slide 2: Introduction Jacob Vaught Page 1
Who is Honicker?
  Specializes in the Manufacturing of Automobile Dashboards
Honicker replaces Senior Management team in 2009
New Management wants to expand rapidly
They Acquire Alpha, Beta, Gamma, Delta
Notes: Honicker= high quality manufacturer of auto dashboards.
Honicker replaces ultra conservative management with new management
Expansion while everyone else is struggling
They have plenty of cash. AA- credit rating
They decided to acquire multiple companies instead of building manufacturing plants and hiring new management teams and employees for each new branch
Acquires 4 companies in different geographical regions
They acquired because it is faster, but after trying to implement a new system, we realized it might have been faster if they built new plants
On average, it takes about 2 years to build a manufacturing plant. It took 168 days to complete tesla Giga Factory in China.

## Slide 3: Introduction Jacob Vaught Page 2
Honicker has an EPM (Enterprise Project Management) system
Honicker wants each company to use the EPM, but a modified version is acceptable also
Problems Arise
  6-month EPM Transition Unsuccessful
  Alpha “Superior EPM”
Notes: EPM = a software?
Timeline had to be updated to 2 years
Alpha wants everyone to use its system because it is supposedly more superior

## Slide 4: Introduction Jacob Vaught Page 3
Problems Arise Cont.
  Trust Issues
  Fear of new system
  Gamma and Delta do not understand their role.
  Different Timelines
  Does not respect Honicker
  Different levels of importance to each company
Notes: EPM = a software?

## Slide 5
Honicker’s strategy involved, consisted of three parts:
  Get all 4 companies to come into agreement on the methodology used.
  Invite clients and stakeholders to see and test the system to provide feedback
  Request 3 representatives with knowledge in project management and authorization per company to make the head decision at the company.
The list of initial problems included:
  Each company saw the importance differently from the others, causing different time schedules.
  Each company was only looking out for themselves, instead of the collaboration being a whole project in sync with the others.
  Different views on the determination of power the Project Manager had, and Gamma and Delta did not understand their roles.
  Alpha Company said they had the better EPM system for all companies to use over Honicker’s EPM system and started to micromanage.
Background Kyle Wagar

## Slide 6: Background Cont. Kyle Wagar
Problems:
Some of the representatives from the other regions were not being truthful/compliant or didn’t want to share what they honestly thought about the whole project and EPM system
2. Each company was being selfish and was looking out more for themselves than the project as a whole in collaboration with the others. They were more willing to see the project fail because of a chance it might affect them positively more so than negatively.
3. the new representatives were worried the new EPM system they had been introduced to would result in a shift of power and authority.
4. Finally, Companies were unsure the new system/project would cause a change in their culture and their connections with others possibly reliant on them.

## Slide 7: Evaluation Aidan Sposato
Overall Goal:
Establish an agreed upon Enterprise Project Management system/mentality
Overarching Problems:
Acquired companies view Honicker as a supply of money, not their new owner
The new companies are apprehensive about changing what has previously been working for them
There is a significant lack of fundamental communication between the companies
Notes: Being a difficult situation, we read through the case study and determined 3 of the biggest issues. It is clear that the overall goal of Honicker is to establish an agreed upon enterprise project management system that will be able to incorporate all of the acquired companies so that they are all working cohesively.
The first problem that needs to addressed is the fact that these acquired companies view Honicker as a supply of money, not their new owners. By acting as if they are their own individual entities, it makes it incredibly difficult for Honicker to establish order and consistency beneath them. This was made clear through the fact that each company had different timelines for the project, and each company also didn’t recognize the importance of it the way Honicker did. We believe this is a result of the senior management from each company believing that they know their clients and stakeholders the best, and their own company's priorities put first.
The second issue is that these new companies are apprehensive about changing what has previously been working for them. The details pointing to this being a problem include:
The management are concerned about losing bonuses in result of increased efficiency and reduced employees
The management do not want to lose all of the power of their own companies and they are against learning a new system
Many employees are concerned that a new system wouldn't work with, or even change the existing company culture
It appears that the companies are not confident Honicker as a whole considering they aren't doing anything to help this difficult situation. Honicker needs to strengthen its relationship with these companies, or they may suffer more dire consequences, such as delays to the timeline.
The third and final problem is insufficient communication between the companies, specifically Gamma and Delta. Gamma and Delta do not seem to understand what is expected of them without someone telling them exactly what is expected. These companies were not at the same project management maturity as the other companies as made apparent by the fact that they had no project management system in place. This may be due to translation errors, but they also seem to either be young companies without a formal management structure or companies that have never expanded much and have never had to improve their project management system. Communication is an important aspect within project management, so it is important that these companies communicate with Honicker to learn their roles and responsibilities.

## Slide 8: Solutions Greg Richard
Establish better lines of communication
Send trusted, knowledgeable Honicker representatives to Gamma and Delta
  Get Gamma and Delta on the right track
  Educate them on Project Management
  "Boots on the ground" to ensure accountability and foster trust and cooperation
  Worth it to train existing management, or replace with management that has prior experience?

## Slide 9: Solutions Cont. Greg Richard
Send Honicker representatives to Alpha and Beta
  Instill trust in Alpha's and Beta's management and shareholders
  Study Alpha's EPM system
  Keep an open mind about Alpha's system
  Adjust EPM if needed to get cooperation from Alpha
  Send reps to Beta to further teach about Project Management

## Slide 10: Solutions Cont. Greg Richard
Most important part is establishing trust!
Force each company to adapt their EPM system
  Adjust if required to satisfy the companies
  Replace Senior level management if necessary
  Use as last resort
Honicker must listen to each company's concerns and compromise where needed
Set up education programs/training courses

## Slide 11: Recommendations Forrest Donnellan
The most desirable solutions for Honicker require acute attention to detail. Representatives must be:
  Experts in Honicker's EPM methodology
  Capable of conflict resolution on a corporate scale
  Involved in the management at Honicker Corp.
    Guarantees trustworthiness and investment into project
Notes: 1a. The Honicker representatives that will be dispatched to its subsidiaries must be experts in Honicker's EPM methodology who have also proven themselves capable of conflict resolution on a corporate scale.

## Slide 12: Recommendations Cont. Forrest Donnellan
Essentials for Honicker
  Transparency (Inform all employees of the policies, relieve uncertainty)
  Sell the overall eventual success of Honicker + its subsidiaries
  Avoid alienation and animosity at all costs
  Recognize if and when success becomes futile
  Prepare confidential exit plans from each company to maximize profit and time saved in the event of contingency

## Slide 13: Recommendations Cont. Forrest Donnellan
Honicker's overall success hinges on its ability to effectively cooperate with 4 unique entities simultaneously
Honicker should prepare for 3 possible outcomes for each subsidiary:
  Cooperation (Embracing Honicker EPM with open arms)
  Resistance (Initial hesitation but eventual successful adoption)
  Separation (Prospect of success futile; subsidiary discarded)