## Sheet1
| Semester | Year | Deliverable
Masters | Summer | 2025 | Capture Rig Developed; Literature Preliminarily Completed. Lake Murray Data captures complete.
| Fall | 2025 | SC/GA/NC Lake Data Captures being completed by undergrads
| Spring | 2026 | Beach/Sea Data Captures being completed baseline Conv1D detector implemented; internal pilot‐data report.
| Summer | 2026 | (Ongoing) Code repo organized; baseline code documented; prepare for comparative study.
| Fall | 2026 | CFAR vs. Conv1D study completed; full conference paper (RadarConf’27) drafted & submitted.
| Spring | 2027 | RadarConf camera-ready delivered; Master’s thesis draft completed.
| Summer | 2027 | Master’s defense passed; pipeline transferred to Ph.D. program; artifacts archived publicly.
PhD | Fall | 2027 | Radar-MAE pre-training done; CVPR ’28 paper drafted & submitted; backbone weights + pip package ready.
| Spring | 2028 | Cross-sensor self-distillation implemented; CVPRW ’28 workshop paper submitted; EO+radar pairs released.
| Summer | 2028 | Few-shot adaptation layer tested (≥ 45 % 5-shot mAP); internal report on few-shot results.
| Fall | 2028 | A-MARV-beta (20 h) dataset collected; Pi-ViT prototype complete; ICASSP ’29 paper drafted & submitted.
| Spring | 2029 | ICASSP ’29 camera-ready; IEEE T-AES journal submission (Radar-MAE + Pi-ViT) completed.
| Summer | 2029 | Thrust C skeleton (shift detection, EWC-R) prototyped; A-MARV annotation plan drafted.
| Fall | 2029 | IEEE T-AES article submitted; shift‐detection + adapter framework implemented; continual‐learning prototype ready.
| Spring | 2030 | Continual‐learning ablation run; CVPRW/NeurIPS ’30 paper on continual adaptation submitted; adapter code + Jupyter dashboards released.
| Summer | 2030 | A-MARV-v1 (30 h) fully annotated; draft of IEEE T-GRS Data Descriptor completed.
| Fall | 2030 | IEEE T-GRS Data Descriptor submitted; loader & baseline packages finalized; dataset + code public release (Zenodo/GitHub).
| Spring | 2031 | Dissertation chapters compiled; mock defense performed; Ph.D. draft ready to file.
| Summer | 2031 | Final Ph.D. defense passed; dissertation PDF filed; final code/data updates (tutorial, dashboard) pushed; “A-MARV Challenge” announced.